## Dashboard
Copyright - Sudharsan Iyengar - August 2017.
Tracking Project Work
| Team Name: |  |  |  |  | Member Contribution |  | Component Effort
Project Description:
| Activity | Time Spent | # of revisits to this activity | Output Artifact (formal and informal) | % of work done by due date | Team Member Name | Total time Spent | Component Name | Total time spent on component
[6 empty] | Steven McVicker | 34+ | Player Views - FrontEnd | 18-20 hrs
| Understanding the problem | 15-20 hrs | 8 |  | 100
[6 empty] | Siddhant Grover | 34+ | Stylepages-FrontEnd | 14-16hrs
| Creating a model for the solution | 4hrs | 5 |  | 100
[6 empty] | Cole Snyder | 42+ | Server-BackEnd | 55-65 hrs
| Writing the Code using an IDE (initial) | 82-86hrs | 25-30 |  | 100
[6 empty] | Andrew Hamlett | 35.25+ | Game Function-BackEnd | 25-35 hrs
| Testing the code - number of runs | 23-25hrs | 15 |  | 100
| Feedback from testing and completion | 10-12hrs | 7 |  | 100

## Component Description
General Description of Components
Name of Component | Brief description of the Component | Team Members responsible
Game board, Index page | A 4*4 grid with Players and their coins | Siddhant Grover(Board)
Player views | Assembling the board with other components on each player's view | Steven Mcvicker and Siddhant Grover and Cole Snyder
Local server | connecting all the players together and sending data throughout using | Cole and Steven Mcvicker
Game Function | The game play functions | Cole and Andrew Hamlett
Node Setup | Used to connect all the players on one local host and send data throughout | Cole
Socket.io and Express setup | Express was the server framework used and socket.io was the asynch method of connecting pages together | Cole

## Understanding the Problem
Understanding the Problem
Date | Component | Member Name | Time spent in minutes | Brief description of output
2019-02-07 | game functions | The brogrammers | 2 hours | Understood the game function as a team and split team responsibilities
2019-02-08 | game board | Siddhant Grover | 1 hour | worked on initial grid and made gui blueprint
2019-02-09 | app.js(localserver) | Cole Snyder | 3 hours | working on different forms of connecting
2019-02-10 | app.js(localserver) | Cole Snyder | 2 hours | Using node
2019-02-11 | app.js(localserver) | Siddhant Grover | 3 hours | self learning and undersatnding node and sockets
2019-02-12 | app.js(localserver) | Andrew Hamlett | 2 hours | breif understanding and setting up app.js
2019-02-12 | app.js(localserver) | Steven Mc Vicker | 2 hours | understanding node.js
2019-02-12 | gui styling | Siddhant Grover | 1 hour | understood the current classes and worked on improving style
2019-02-13 | player view | Steven Mc Vicker | 1 hour | understanding the blueprint of gui and working on styling
2019-02-16 | game functions | Andrew Hamlett | 1.5 hours | working on different objects and classes needed for gameplay
2019-02-16 | game functions | Cole Snyder | 1 hour | connecting all the players on the server
2019-02-20 | replicating the view to all players | Steven Mc Vicker | 1 hour | making sure a change on one view reflects on all
2019-02-23 | game logic and points | The brogrammers | 1 hour | understanding and working on point system and winner
2019-02-25 | connection .js | Andrew Hamlett | 2hrs | getting the winner
2019-02-25 | connection.js | Cole Snyder | 2hrs | winner
2019-02-25 | player views | Steven Mcvicker | 2hrs | adding ids and changing buttons
2019-02-25 | player buttons | Siddhant Grover | 2 hrs | sending the numbers across and manipulating divs
2019-02-28 | connection.js and app.js | Andrew Hamlett | 1 hr | getting the winner after all rounds
2019-02-28 | conection.js and app.js | Cole Snyder | 1 hrs | gettignthe right winner

## Creating the Model
Creating the Model
Date | Component | Member Name | Time spent in minutes | Brief description of output
2019-02-08 | Front End | Steve and Sid | 1hr | talking about what we need ,and how we should implement it
2/13/2019 | Back End | Cole and Andrew | 2hrs | talking about what are we going to have on our back end as well as how to build the connection
2019-02-20 |  | The Brogrammers | 2hrs | connecticng the front end to back end and adding further entities

## Writing Code
Writing code
Date | Component | Member Name | Time spent in minutes | Brief description of output
2/9/2019-2/11/19 | Game Board | Siddhant Grover | 3hrs | Get a working gameboard
2/13/2019-2/15/19 | app.js | Cole Snyder | 4.5 hrs | Setting up a local server to connect between the players
2/13/2019-2/15/19 | player view | Steven Mcvicker | 4 hrs | Adding buttons,style,player points,and numbers
2/14/2019-2/17/19 | Game Functions | Andrew Hamlett | 3hrs | Create classes, objects etc.
2/14/2019-2/15/19 | app.js | Cole Snyder | 2 hrs | sending the server side data
2019-02-15 | app.js | Andrew Hamlett | 1.5hrs | Experimental branching
2019-02-17 | Index page | Siddhant Grover | 2hrs | styling pages
2/17/2019-2/19/2-19 | app.js | Steven Mcvicker | 3hrs | player queue and join handling
2/17/2019-2/19/2019 | connection.js | Cole Snyder | 3.5hrs | player queue and join handling
2/17/2019-2/19/2019 | connection.js | Andrew Hamlett | 2hrs | Filling player hands,giving random numbers,etc.
2019-02-18 | connection.js | The Brogrammers | 5hrs | transferring the data through sockets and builduing new methods on the server side to keep track of the gameplay
2/21/19-2/24/19 | app.js | Steven and Cole | 14 hrs | back end support ,controlling and sequentially ordering player moves
2/22/9-2/26 | connection.js | Andrew and Sid | 16hrs | accessing dom,connecting the changes taking place to the Gui
2/27/19-3/1/19 | app.js | Cole and Steve | 15-17hrs | point system and winner

## Testing the code - # of runs
Testing the code - # runs per session
Date | Component | Member Name | Time spent in minutes | Brief description of output
2019-02-12 | Game Board | Steven,Cole and Andrew | 35-40min | checked the gui,gave suggestions,and ideas that will makeboard manipulation easy(2 runs)
2019-02-15 | app.js | Sid,Andrew and Steve | 2 hrs | focus on socket as well as give futher ideas to connect all 4 throught different screens(4runs)
2019-02-16 | player view | Cole,Andrew and Sid | 2 hour | give ideas for better styling,using a formal grid ,and more ideas to connect to backend(2runs)
2019-02-18 | index page | Cole and Steve | 1.5 hrs | gave ideas for consistent style(1run)
2019-02-20 | Game functions | Steven and Sid | 2 hrs | check player,their hands,player array,etc.(3runs)
2019-02-22 | app.js | Steven ,Andrew and Sid | 2.5 hrs | checking the gameplay order,sequence as well as number additions(5runs)
2\25/2019 | connection.js | Sid,Cole ,and Steve | 3 hrs | more testing on different functions and setting the board(3runs)
2019-02-27 | game testing(without rounds and points) | The Brogrammers | 3 hrs | seeing the functionong of the whole game,adding different numbers to player(6 run)
3/1/2018-3/3/2019 | Whole game testing | The Brogrammers | 8-12 hrs | playing the game in different scenarios ie adding different players,making different subsets,trying to lose,triying to win,all different scenarios(15 runs)

## Revisions based on Testing
Revisions based on Testing
Date | Component | Member Name | Time spent in minutes | Brief description of output
2019-02-13 | Game board | Siddhant G | 25 min | using more contrasting colors
2019-02-16 | connection.js and app,js | Cole S | 1hr | changing local server means
2/17-2/18/19 | Player view and index page | Steven and Sid | 2hr | change some styling,adding better background,better looking coins etc
2/20/19-2/23/19 | connection.js | Cole amd Steve | 1.5 hr | making sure the players are connected and checking if all the players come together in the array with all their numbers chosen
2/24/19-2/26/19 | connection.js | Steven and Cole | 2.5 hrs | adding the Game functions to connection.js so that all data can be tracked
2019-02-28 | gameplay | Andrew and Sid | 2.5 hrs | make buttons look better and add player wins
3/2/19-3/3/10 | gameplay | Steven ,and Andrew | 3 hrs | player rounds and determining winner and adding 10 points to each non winner.